TamamHealth — Summer 2026

Full Team Plan

One working hospital, end to end, by 30 June — then deploy, prove, and grow.

# The North Star

By 30 June, one real hospital runs entirely on TamamHealth — every level of the patient journey, from the front desk to the dispensing window. A patient should be able to walk in, be registered, triaged, seen by a clinician, sent for labs, prescribed and dispensed medication, billed, and discharged — with every step captured in the system, working offline, on the hospital's own devices. Allen leads with a brand and logo refresh and a redesign of the platform; engineering builds the redesigned flow behind it; clinical research makes sure it matches how a hospital actually works. Everything else this summer builds on that one proven system.

July is for deploying it in the real hospital, training staff, and hardening it under real use. August is for expanding — more departments and levels, marketing the proof, and raising the funding to scale into the fall.

# The Team & Where Each Person Leads

Eight people, clear lanes, one deadline. Toye keeps the whole thing on schedule; everyone else owns a workstream and supports the June crunch.

| Member | Role | Summer focus |
| --- | --- | --- |
| Teny Makuach | All-rounded / Founder | Product vision and final calls; fills gaps across engineering, design, clinical, and ops; owns the hospital relationship and stakeholder/funder conversations alongside Ekow. |
| Toye Adebayo | Project Manager | Runs the sprint board, standups, and timeline; protects the 30-June scope; unblocks the team and owns cross-functional handoffs (design → eng → clinical sign-off). |
| Allen Wang | UI/UX Designer | Refreshes the logo and brand first, then redesigns the platform UX/UI module by module and builds the shared design system. Design is the long pole — Allen sets the pace. |
| Isaac Kyalo | Technical Lead | Owns architecture, the build plan, code review, offline/sync reliability, and deployment to the hospital. Splits the patient-flow modules with Mark. |
| Mark Duso | Software Engineer | Implements the redesigned patient-flow modules, wires them end to end, writes tests, and fixes what UAT surfaces. |
| Chinonye Hycent | Clinical Research | Defines the golden patient flow with real clinicians; validates clinical content (triage, ICD-11, drug lists, protocols); runs user-acceptance testing and clinical sign-off. |
| Ekow Williams | Community, Partnerships & Fundraising | Secures the pilot hospital and its MoU; builds provider/NGO relationships; runs the funding pipeline (grants and donors) to resource July–August and the fall. |
| Diing Lual | Marketing & Outreach | Launches the refreshed brand publicly; builds the content engine and channels; turns the hospital go-live into proof — stories, demos, and the website. |

The June Deliverable

# What “Done” Means: One Hospital, Front Desk to Dispensing

“Finished” is not a feature list — it is a patient walking the full journey without leaving the system or falling back to paper. This is the golden flow we are shipping. Each step already exists as a module in the platform; June is about redesigning, connecting, and hardening them into one seamless hospital workflow.

| Step | Who runs it | What happens in TamamHealth |
| --- | --- | --- |
| 1. Registration | Front-desk clerk | Register or find the patient (Master Patient Index), capture demographics, photo/QR ID, and insurance — no national ID required. |
| 2. Triage | Nurse | Record vitals, chief complaint, and priority; queue the patient for the right clinician. |
| 3. Consultation | Doctor / clinician | Clinical note (SBAR), AI-assisted diagnosis with ICD-11 coding, problem list, and orders for labs and medication. |
| 4. Diagnostics | Lab technician | Receive lab orders, enter results, and return them to the patient record for the clinician to review. |
| 5. Pharmacy / dispensing | Pharmacist | See the prescription, run the drug-interaction check, dispense, and update stock. |
| 6. Billing & payment | Cashier / billing | Apply charges, check eligibility, take payment, and issue a receipt. |
| 7. Records & discharge | Clinician / clerk | Visit summary, referral if needed, follow-up booking, and patient-portal access — all synced when connectivity returns. |

Non-negotiable through every step: it works offline, every entry is saved and syncs reliably, and privacy and access controls hold at each role.

Workstreams

# How the Work Splits

Design — Allen (the long pole)

- Week 1: Logo and brand refresh — finalize the wordmark, heart mark, color tokens, and type, and the app icon.

- Weeks 1–3: Redesign the seven flow screens in priority order (registration → triage → consultation → lab → pharmacy → billing → discharge) and build the shared component library so engineering reuses, not rebuilds.

- Continuous: Daily handoff to Isaac and Mark; accessibility (WCAG AA), large tap targets, icon-driven patterns for low-literacy staff.

Engineering — Isaac (lead) + Mark

- Isaac: Architecture and sequencing, code review, offline/sync conflict handling, hospital configuration and deployment, technical sign-off.

- Mark: Implement the redesigned modules against the new component library, wire the flow end to end, write tests, fix UAT bugs.

- Both: Keep the demo/staging stack green so clinical and partners can review at any time.

Clinical Research — Chinonye

- Sit with real clinicians to validate the golden flow against how the target hospital actually operates.

- Confirm clinical content: triage rules, ICD-11 sets, drug list and interactions, lab catalogue, and consult templates.

- Own user-acceptance testing in Week 4 and the clinical go/no-go sign-off.

Partnerships & Fundraising — Ekow

- Lock the pilot hospital and a signed MoU early — engineering needs the real target to configure against.

- Build the provider, NGO, and Ministry relationships that make July deployment smooth.

- Run the funding pipeline (grants + donors) so July–August and the fall are resourced.

Marketing & Outreach — Diing

- Roll out the refreshed brand publicly and stand up the channels (Instagram, TikTok, YouTube, LinkedIn).

- Build the content engine; document the build and the go-live as proof, not hype.

- Polish the website around the new brand and the hospital case study.

Project Management — Toye  /  Founder — Teny

- Toye: Sprint board, daily standups, weekly demo, scope control, and the single source of truth on status and blockers.

- Teny: Floats to wherever the crunch is — code, design QA, clinical, content, or the hospital relationship — and makes the product calls.

June — The Build Sprint

# June, Week by Week (2–30 June)

Four one-week sprints. Each ends with a working demo of everything built so far. The flow is built in the order a patient walks it, so there is always an end-to-end path to test.

| Week | Goal | Who drives |
| --- | --- | --- |
| Wk 1 · 2–8 Jun | Foundations: logo + brand refresh; design system kickoff; lock the pilot hospital; audit existing modules; configure the hospital; design registration + triage. | Allen (brand/design), Ekow (hospital), Isaac (config/audit), Chinonye (flow definition) |
| Wk 2 · 9–15 Jun | Build the front of the flow: registration → triage → consultation redesigned and working end to end on staging. | Allen (consultation/lab design), Mark + Isaac (build), Chinonye (content) |
| Wk 3 · 16–22 Jun | Build the back of the flow: labs → pharmacy/dispensing → billing; connect the whole journey; offline + sync hardening. | Mark + Isaac (build), Allen (billing/discharge design), Toye (integration tracking) |
| Wk 4 · 23–30 Jun | Lock it: full end-to-end UAT with clinicians, bug-fix, accessibility + performance pass, deploy to the hospital, clinical go/no-go. | Chinonye (UAT/sign-off), Isaac (deploy), Mark (fixes), Diing (capture go-live) |

Scope discipline: if something is not on the front-desk-to-dispensing path, it waits for July. Toye guards this line.

July — Deploy & Prove

# July: Make It Real

- Deploy in the hospital for daily use; train front-desk, nursing, clinical, lab, pharmacy, and billing staff.

- Run a support loop: watch real usage, fix friction fast, harden offline reliability and sync under real load.

- Turn the patient app and web portal on for this hospital's patients (records, results, reminders).

- Marketing: publish the first hospital story and staff/patient testimonials; Ekow advances the funding conversations with live proof.

August — Expand & Raise

# August: Grow on Proof

- Extend beyond the core flow: more departments, referrals, maternal/child, surveillance, and DHIS2 reporting for this hospital.

- Line up the next site(s) and lower-level facilities (PHCU / Boma) to show the five-level vision in action.

- Convert the proof into funding and partnerships; publish the case study; plan the fall rollout.

# Definition of Done — the June Product

- A patient can be taken from registration to dispensing and discharge entirely in TamamHealth, with no paper fallback.

- Every staff role along the flow has a redesigned screen that works offline and shows clear sync status.

- Data entered offline syncs reliably and survives conflicts; nothing is lost.

- Role-based access and privacy hold at each step; refreshed brand applied throughout.

- Clinical research has signed off, and the system is deployed on the hospital's devices.

# Success Metrics

June: the golden flow demoably works end to end; clinical sign-off achieved; deployed to one hospital. Across the summer, watch: patients taken fully through the flow in-system; share of visits captured without paper; offline entries successfully synced; staff trained per role; time per step vs. the old paper process; bugs open vs. closed; brand/UX coverage across screens; marketing reach and demo requests; funding pipeline advanced; and qualitative trust feedback from real staff and patients.

# Risks, Dependencies & Decisions Needed

| Risk / dependency | Mitigation |
| --- | --- |
| Design is the long pole and gates engineering | Allen prioritizes flow screens in patient-journey order; ship screen-by-screen so eng is never idle; Teny helps with design QA. |
| Pilot hospital not locked early | Ekow + Teny close the hospital and MoU in Week 1 — engineering must configure against the real target. |
| Scope creep past the core flow | Toye enforces the front-desk-to-dispensing line; anything else is a July item. |
| Offline/sync edge cases surface late | Isaac builds and tests offline from Week 1, not at the end; Week 4 includes a dedicated hardening pass. |
| Clinical mismatch with real workflow | Chinonye validates with clinicians from Week 1 and owns Week-4 UAT and sign-off. |

Decisions needed up front

- Which hospital, and which level (county / state / teaching) — this sets the configuration and the staff roles in scope.

- Which devices the hospital will use (shared tablets, phones) — drives the redesign and testing targets.

- Confirm the exact roles to support at go-live (front desk, nurse, doctor, lab, pharmacy, billing, admin).

# Cadence & Tools

Daily standup (15 min) and a weekly Friday demo of the working flow. Toye runs the board; design → engineering → clinical handoffs are tracked there. Engineering works in Git/GitHub with code review and CI; design lives in Figma with continuous handoff. For the full technology stack, see the companion “TamamHealth — Tools & Software” document.

This is a working plan. The 30-June goal and the front-desk-to-dispensing scope are fixed; how we get there is open to the team's judgment as we learn.

www.tamamhealth.com